## Sheet1
LoRa Timeline and efforts
Planned hours:
Hardware | 250hrs
Firmware | 300hrs
Milestone | S.No | Activity | Owner | Planned Hours | Actual hours | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-10 | 2024-03-11 | 2024-03-12
[6 empty] | WEEK1 | [6 empty] | WEEK2 | [6 empty] | WEEK3 | [6 empty] | WEEK4 | [6 empty] | WEEK5 | [6 empty] | WEEK6 | [6 empty] | WEEK7 | [6 empty] | WEEK8 | [6 empty] | WEEK9 | [6 empty] | WEEK9 | [6 empty] | WEEK10 | [6 empty] | WEEK11 | [6 empty] | WEEK12
Concept/ study phase | 1 | Project objective defining
| 2 | Study on Lora Module and its real time application
| 3 | Preparing PRD , Timeline and its efforts
| 4 | Hardware architecture and firmware Architecture (Flowchart)
| 5 | Component/ module selection, module procurement
| 6 | Sample project selection (study), case study prepare
| 7 | Lora module testing and validation(firmware and hardware)
| 8 | Individual Lora module functionality check and validation
| 9 | Individual GPS module functionality validation
| 10 | Lora and GPS module integration with microcontroller
| 11 | Sensor data transmission using sx1262 transmitter
| 12 | Internal demo and validation approval(transreceiver-Sx1262,GPS)
| 13 | Microcontroller selection
| 14 | Micro controller selection review
| 15 | Lora IC ,antenna and its passives selection
| 16 | GPS IC,antenna and its passives selection
| 17 | Power section selection
| 18 | Lora, GPS IC , Antenna, power section Selection review
Engineering phase | 19 | Schematics design
| 20 | Schematic design internal review -1st review
| 21 | Schematic design internal review-2nd review
| 22 | layout design outsourcing and followups
| 23 | Layout design external review -1st review
| 24 | Layout design external review - 2nd review
| 25 | PCB fabrication release
| 26 | EE components ordering and follow up
| 27 | EE components Segregation
| 28 | EE Components assembly on PCB
| 29 | PCB board bring up - Power section validation
| 30 | PCB board bring up - Lora IC and its sub part validation
| 31 | PCB board bring up - GPS IC and its sub part validation
| 32 | Pcb board bring up with full functionality ( Hardware)
| 33 | PCB bring up and firmware intergration
| 34 | Full fuctionality check
| 35 | Documentation
| 36 | Real time testing and demo